## Todos
Capsule Networks
Type | Subtask of | Task List | Name | Description | Created By | Date Created | Assigned To | Priority | Status | Start Date | Due Date | Date Completed | Project Group | Project | Raw Description | Milestone | Milestone Description | Milestone Due Date | Milestone Status | Milestone Priority | Milestone Assigned To | Milestone Tags | Last Comment | Last Comment By | Last Comment Date | Url | Tags
Task |  | Learning Phase | Read the official paper | To familiarize ourselves with the architecture | Hemanth Reddy | 2020-11-02 13:33 | Everyone | None | Completed |  | 2020-10-02 | 2020-10-02 | Team Ace | Capsule Networks | <p>To familiarize ourselves with the architecture</p> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35752386
Task |  | Learning Phase | Understand Dynamic routing by agreement |  | Hemanth Reddy | 2020-11-05 11:58 | Everyone | Medium | Completed |  | 2020-10-06 | 2020-10-06 | Team Ace | Capsule Networks | [11 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833612
¦-Subtask | Understand Dynamic routing by agreement | Learning Phase | Youtube tutorials of Aurelien on Capsnet |  | Hemanth Reddy | 2020-11-05 11:59 | Unassigned | None | Completed |  |  | 2020-11-05 | Team Ace | Capsule Networks | [11 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833619
¦-Subtask | Understand Dynamic routing by agreement | Learning Phase | Medium Articles and tutorials |  | Hemanth Reddy | 2020-11-05 11:59 | Unassigned | None | Completed |  |  | 2020-11-05 | Team Ace | Capsule Networks | [11 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833621
Task |  | Implementation on MNIST | Study MNIST dataset | Study MNIST dataset and complete literature survey on state-of-art existing models | Hemanth Reddy | 2020-11-05 12:05 | Hemanth Reddy | High | Completed |  | 2020-10-13 | 2020-10-13 | Team Ace | Capsule Networks | <p>Study MNIST dataset and complete literature survey on state-of-art existing models</p> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833656
Task |  | Implementation on MNIST | Implement MNIST on pre-existing architectures | Implement MNIST on pre-defined architectures such as CNN Densenet121 Densenet151 Resnet18 | Hemanth Reddy | 2020-11-05 12:28 | Hemanth Reddy | Medium | Completed |  | 2020-10-20 | 2020-10-20 | Team Ace | Capsule Networks | <p>Implement MNIST on pre-defined architectures such as </p> <ul> <li>CNN</li> <li>Densenet121</li> <li>Densenet151</li> <li>Resnet18</li> </ul> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833815
Task |  | Implementation on MNIST | Implement MNIST on Capnet | Implement Capnet on MNIST by using standard hyperparameters mentioned in the Paper | Hemanth Reddy | 2020-11-05 12:29 | Hemanth Reddy | High | Completed |  | 2020-10-24 | 2020-10-24 | Team Ace | Capsule Networks | <p>Implement Capnet on MNIST by using standard hyperparameters mentioned in the Paper</p> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833835
Task |  | Implementation on MNIST | Implementation by varying the hyper-parameters | Training samples Changes the epochs batch size normalisation learning rate | Hemanth Reddy | 2020-11-05 12:31 | Hemanth Reddy | High | Completed |  | 2020-10-28 | 2020-10-28 | Team Ace | Capsule Networks | <ul> <li>Training samples</li> <li>Changes the epochs</li> <li>batch size</li> <li>normalisation</li> <li>learning rate</li> </ul> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833846
Task |  | Implementation on Fashion-MNIST | Study Fashion-MNIST dataset | Study Fashion-MNIST dataset and complete literature survey on state-of-art existing models | Rahul Gite | 2020-11-05 12:34 | Rahul Gite | High | Completed |  | 2020-10-13 | 2020-10-13 | Team Ace | Capsule Networks | <p>Study Fashion-MNIST dataset and complete literature survey on state-of-art existing models</p> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833876
Task |  | Implementation on Fashion-MNIST | Implement Fashion-MNIST on pre-existing architectures | Implement Fashion-MNIST on pre-defined architectures such as CNN Densenet121 Densenet151 Resnet18 | Rahul Gite | 2020-11-05 12:37 | Rahul Gite | Medium | Completed |  | 2020-10-20 | 2020-10-20 | Team Ace | Capsule Networks | <p>Implement Fashion-MNIST on pre-defined architectures such as </p> <ul> <li>CNN</li> <li>Densenet121</li> <li>Densenet151</li> <li>Resnet18</li> </ul> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833912
Task |  | Implementation on Fashion-MNIST | Implement Fashion-MNIST on CapsNet | Implement Capnet on Fashion-MNIST by using standard hyperparameters mentioned in the Paper | Rahul Gite | 2020-11-05 12:39 | Rahul Gite | High | Completed |  | 2020-10-24 | 2020-10-24 | Team Ace | Capsule Networks | <p>Implement Capnet on Fashion-MNIST by using standard hyperparameters mentioned in the Paper</p> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833922
Task |  | Implementation on Fashion-MNIST | Implementation by varying the hyper parameters | The following hyper parameters are to be changed and checked: Training samples Changes the epochs batch size normalisation learning rate | Rahul Gite | 2020-11-05 12:41 | Rahul Gite | High | Completed |  | 2020-10-28 | 2020-10-28 | Team Ace | Capsule Networks | <p>The following hyper parameters are to be changed and checked:</p> <ul> <li>Training samples</li> <li>Changes the epochs</li> <li>batch size</li> <li>normalisation</li> <li>learning rate</li> </ul> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833951
Task |  | Implementation on CIFAR10 | Study CIFAR 10 dataset |  | Rishi Sharma | 2020-11-05 12:37 | Unassigned | High | Completed |  | 2020-10-13 | 2020-10-13 | Team Ace | Capsule Networks | [11 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833907
Task |  | Implementation on CIFAR10 | Implement CIFAR 10 on pre-existing architectire |  | Rishi Sharma | 2020-11-05 12:38 | Unassigned | Medium | Completed |  | 2020-10-20 | 2020-10-20 | Team Ace | Capsule Networks | [11 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833915
Task |  | Implementation on CIFAR10 | Implement CIFAR 10 on Capsnet |  | Rishi Sharma | 2020-11-05 12:39 | Unassigned | High | Completed |  | 2020-10-24 | 2020-10-24 | Team Ace | Capsule Networks | [11 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833920
Task |  | Implementation on CIFAR10 | Hyper parameter tuning of the Capsnet Architecture |  | Rishi Sharma | 2020-11-05 12:40 | Unassigned | High | Completed |  | 2020-10-28 | 2020-10-28 | Team Ace | Capsule Networks | [11 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833929
Task |  | Conclusion and Final phase | Comparison of Capnet results | Compare results of Capnet on MNIST FMNIST CIFAR and understand the performance on each dataset and make a report | Hemanth Reddy | 2020-11-05 12:38 | Everyone | High | Completed |  | 2020-11-02 | 2020-11-02 | Team Ace | Capsule Networks | <p>Compare results of Capnet on</p> <ul> <li>MNIST</li> <li>FMNIST</li> <li>CIFAR</li> </ul> <p>and understand the performance on each dataset and make a report</p> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833914
Task |  | Conclusion and Final phase | Comparison of architectures | We compare the results of different datasets on different architectures and make a report Capnet Densenet151 Densenet121 Resnet CNN | Hemanth Reddy | 2020-11-05 12:39 | Everyone | Medium | Completed |  | 2020-11-02 | 2020-11-02 | Team Ace | Capsule Networks | <p>We compare the results of different datasets on different architectures and make a report</p> <ul> <li>Capnet</li> <li>Densenet151</li> <li>Densenet121</li> <li>Resnet</li> <li>CNN</li> </ul> <p></p> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833924
Task |  | Conclusion and Final phase | Exploring variants of Capnet | Exploring variants of Capnet available in the literature and analysing the areas of improvements DCNet DCNet++ 3-Level Capnets DeepCaps Deepfeat-Caps | Hemanth Reddy | 2020-11-05 12:44 | Everyone | Low | Completed |  | 2020-11-09 | 2020-11-07 | Team Ace | Capsule Networks | <p>Exploring variants of Capnet available in the literature and analysing the areas of improvements</p> <ul> <li>DCNet</li> <li>DCNet++</li> <li>3-Level Capnets</li> <li>DeepCaps</li> <li>Deepfeat-Caps</li> </ul> | [10 empty] | https://freedcamp.com/Team_Ace_AMf/Capsule_Networks_T5H/todos/35833970